## Sheet1
PHASE | TASK | ASSIGNEE | START DATE | END DATE
Conception & Initation | Team Contract | All | 2025-08-25 | 2025-09-21
Definition & Planning | GitHub Creation | Tyler Meiners | 2025-09-22 | 2025-09-29
Definition & Planning | Project Plan | Maria Montgomery | 2025-09-22 | 2025-09-29
Definition & Planning | WebHost Selection | Zachary Davis | 2025-09-29 | 2025-10-06
Definition & Planning | Prototype Selection | Maria Montgomery | 2025-09-29 | 2025-10-06
Definition & Planning | Programming Language Selection | All | 2025-09-29 | 2025-10-06
Definition & Planning | Weekly Meeting Setup | Tyler Meiners | 2025-09-29 | 2025-10-06
Definition & Planning | Identify Cybersecurity role(s) and task(s) to be gamified | All | 2025-09-30 | 2025-10-06
Execution (Phase 1) | Design Wireframe for Role 1, Task 1 | Maria Montgomery | 2025-10-13 | 2025-10-20
Execution (Phase 1) | Design Wireframe for Role 1, Task 2 | Maria Montgomery | 2025-10-21 | 2025-10-27
Execution (Phase 1) | Design Wireframe for Role 1, Task 3 | Maria Montgomery | 2025-10-28 | 2025-11-03
Execution (Phase 1) | Design Workflow for Role 1 | Maria Montgomery | 2025-11-04 | 2025-11-10
Execution (Phase 1) | Design Wireframe for Role 2, Task 1 | Tyler Meiners | 2025-10-13 | 2025-10-20
Execution (Phase 1) | Design Wireframe for Role 2, Task 2 | Tyler Meiners | 2025-10-21 | 2025-10-27
Execution (Phase 1) | Design Wireframe for Role 2, Task 3 | Tyler Meiners | 2025-10-28 | 2025-11-03
Execution (Phase 1) | Design Workflow for Role 2 | Tyler Meiners | 2025-11-04 | 2025-11-10
Execution (Phase 1) | Design Wireframe for Role 3, Task 1 | Zachary Davis | 2025-10-13 | 2025-10-20
Execution (Phase 1) | Design Wireframe for Role 3, Task 2 | Zachary Davis | 2025-10-21 | 2025-10-27
Execution (Phase 1) | Design Wireframe for Role 3, Task 3 | Zachary Davis | 2025-10-28 | 2025-11-03
Execution (Phase 1) | Design Workflow for Role 3 | Zachary Davis | 2025-11-04 | 2025-11-10
Execution (Phase 1) | Design Wireframe for Role 4, Task 1 | Adonay Kebede | 2025-10-13 | 2025-10-20
Execution (Phase 1) | Design Wireframe for Role 4, Task 2 | Adonay Kebede | 2025-10-21 | 2025-10-27
Execution (Phase 1) | Design Wireframe for Role 4, Task 3 | Adonay Kebede | 2025-10-28 | 2025-11-03
Execution (Phase 1) | Design Workflow for Role 4 | Adonay Kebede | 2025-11-04 | 2025-11-10
Execution (Phase 2) | Program UI | All | 2025-11-11 | 2025-11-17
Execution (Phase 2) | Program Role 1, Task 1 | Maria Montgomery | 2025-11-18 | 2025-12-01
Performance and Control | System Testing | Maria Montgomery | 2025-12-08 | 2025-12-15
Execution (Phase 2) | Program Role 2, Task 1 | Tyler Meiners | 2025-11-18 | 2025-12-01
Performance and Control | System Testing | Tyler Meiners | 2025-12-08 | 2025-12-15
Execution (Phase 2) | Program Role 3, Task 1 | Zachary Davis | 2025-11-18 | 2025-12-01
Performance and Control | System Testing | Zachary Davis | 2025-12-08 | 2025-12-15
Execution (Phase 2) | Program Role 4, Task 1 | Adonay Kebede | 2025-11-18 | 2025-12-01
Performance and Control | System Testing | Adonay Kebede | 2025-12-08 | 2025-12-15
Performance and Control | Integrate All Roles, Task 1 | All | 2026-01-12 | 2026-01-19 | *New Semester
Execution (Phase 2) | Program Role 1, Task 2 | Maria Montgomery | 2026-01-20 | 2026-02-02
Performance and Control | System Testing | Maria Montgomery | 2026-02-03 | 2026-02-09
Execution (Phase 2) | Program Role 2, Task 2 | Tyler Meiners | 2026-01-20 | 2026-02-02
Performance and Control | System Testing | Tyler Meiners | 2026-02-03 | 2026-02-09
Execution (Phase 2) | Program Role 3, Task 2 | Zachary Davis | 2026-01-20 | 2026-02-02
Performance and Control | System Testing | Zachary Davis | 2026-02-03 | 2026-02-09
Execution (Phase 2) | Program Role 4, Task 2 | Adonay Kebede | 2026-01-20 | 2026-02-02
Performance and Control | System Testing | Adonay Kebede | 2026-02-03 | 2026-02-09
Performance and Control | Integrate All Roles, Task 2 | All | 2026-02-10 | 2026-02-16
Execution (Phase 2) | Program Role 1, Task 3 | Maria Montgomery | 2026-02-17 | 2026-02-23
Performance and Control | System Testing | Maria Montgomery | 2026-02-24 | 2026-03-02
Execution (Phase 2) | Program Role 2, Task 3 | Tyler Meiners | 2026-02-17 | 2026-02-23
Performance and Control | System Testing | Tyler Meiners | 2026-02-24 | 2026-03-02
Execution (Phase 2) | Program Role 3, Task 3 | Zachary Davis | 2026-02-17 | 2026-02-23
Performance and Control | System Testing | Zachary Davis | 2026-02-24 | 2026-03-02
Execution (Phase 2) | Program Role 4, Task 3 | Adonay Kebede | 2026-02-17 | 2026-02-23
Performance and Control | System Testing | Adonay Kebede | 2026-02-24 | 2026-03-02
Performance and Control | Integrate All Roles, Task 3 | All | 2026-03-03 | 2026-03-09
Project Close | Create Presentation | All | 2026-03-10 | 2026-03-16
Project Close | Write Paper | All | 2026-03-17 | 2026-03-23
Project Close | Film Presentation and Demo | All | 2026-03-24 | 2026-03-31